## Summary
CHCG EnableOS Development Plan Summary
Planning Context
The platform now has a persuasive, client-demo-ready foundation across learner, coach, manager, executive, admin, reporting, and content-library experiences.
At the same time, there is still substantial work remaining in three major tracks: UI/UX consistency and polish, functional depth for real operations, and migration of the full CHCG training curriculum into the LMS.
Recommended sequencing is to complete the curriculum/content plan, then run a unified UI and responsiveness pass, then finalize production-grade operational features such as SSO, live reporting integrations, exports, notifications, and admin management tooling.
Metric | Value | Notes
Current position | Strong demo-quality foundation with significant remaining work to reach production depth. | The product already demonstrates multi-role workflows, guided training, coaching, content exploration, and reporting.
Major completed milestone groups | 18 grouped foundations delivered | Completed items are intentionally summarized as milestone themes rather than hundreds of individual tasks.
Current sprint focus | Packaging, training-flow polish, content-library stabilization, and coaching modal follow-up | These items keep the current demo stable while clarifying next-stage priorities.
Largest remaining workstream | Full curriculum migration into all 7 modules | This is the most substantial remaining effort across learner and leadership training tracks.
Additional high-priority gaps | UI consistency, mobile responsiveness, enterprise auth/SSO, live data integration, admin tools, accessibility | These items define the difference between a compelling demo and a production-ready platform.
Planning note | All estimates are directional planning ranges, not fixed implementation commitments. | Actual effort will depend on curriculum source quality, stakeholder revision cycles, and production integration requirements.

## Development Plan
Area | Item | Status | Priority | Est. Hours | Notes
Completed Foundation | Core full-stack application foundation established with React 19, Tailwind 4, Express, tRPC, Drizzle, tenant-aware data model, and Manus OAuth integration. | Completed | Completed | Delivered | The platform now has a stable demo-ready technical base that can support continued feature expansion.
Completed Foundation | Role-based workspace framework delivered for learner, coach, manager, executive, admin, reporting, and content-facing experiences. | Completed | Completed | Delivered | Primary navigation, route access, and role-specific shells are in place.
Completed Foundation | Mission-control UI shell created with collapsible sidebar, compact headers, shared visual language, and lower-scroll workspace patterns. | Completed | Completed | Delivered | This provides the design system direction, but a broader consistency pass is still recommended.
Completed Foundation | Learner training experience converted from stacked scroll-heavy sections into guided page-by-page progression with contextual navigation. | Completed | Completed | Delivered | Improves orientation and reduces visual fatigue during training.
Completed Foundation | Interactive flash-card brief system redesigned across Training Zone and Content Missions, including composition cleanup and jump-strip navigation. | Completed | Completed | Delivered | Brief content is more navigable and visually cleaner than the previous fragmented layout.
Completed Foundation | Coach workspace refined with visible coaching-log launch actions and a focused reusable pop-up flow for structured log entry. | Completed | Completed | Delivered | The coach ribbon interaction was restored and validated after a visibility regression.
Completed Foundation | Manager workspace expanded with a shared coaching-log modal path so coaching actions can occur without leaving the current context. | Completed | Completed | Delivered | Supports role continuity and reuse of shared coaching components.
Completed Foundation | Content Missions redesigned into a cleaner training-library style experience with focused launch behavior for selected learning content. | Completed | Completed | Delivered | Reduces clutter and creates a more intentional content-entry experience.
Completed Foundation | Content Missions explorer regression repaired so track cards, filters, and text hierarchy render clearly again. | Completed | Completed | Delivered | This closed a visible presentation issue that undermined client demos.
Completed Foundation | Reporting workspace established with executive-facing proof, ROI, error-rate, question, lifecycle, cohort, and benchmarking views. | Completed | Completed | Delivered | Creates a strong narrative for client-facing analytics demonstrations.
Completed Foundation | Executive dashboard strengthened with tenure-aware lifecycle reporting, proof-of-impact framing, coaching consistency, and behavior-analysis insights. | Completed | Completed | Delivered | These are persuasive demo surfaces, though live production data integration remains future work.
Completed Foundation | Question-level readiness and performance intelligence added, including miss-rate trends, first-pass success, and high-alert risk states. | Completed | Completed | Delivered | Supports evidence-led conversations about training effectiveness.
Completed Foundation | Learner journey and assigned re-engagement flows refined with stronger wording, improved readability, and better transition behavior. | Completed | Completed | Delivered | Includes terminology updates and completion-state improvements.
Completed Foundation | Training quiz and knowledge-check interfaces reformatted for cleaner spacing, stronger readability, and a more modern instructional feel. | Completed | Completed | Delivered | Important groundwork for curriculum expansion, but more instructional-content depth is still needed.
Completed Foundation | Role-scoped navigation and access behavior tightened so learner experiences are better isolated from coach, manager, admin, and executive areas. | Completed | Completed | Delivered | Helps preserve a more credible multi-role demo path.
Completed Foundation | Training brief completion, coaching-log save, and related learner/coach regressions repaired and validated. | Completed | Completed | Delivered | Stabilized several high-visibility flows that had previously blocked demos.
Completed Foundation | Targeted regression coverage expanded across training layout, flash-card briefs, coaching popups, reporting surfaces, and content-library behavior. | Completed | Completed | Delivered | Automated validation supports safer future UI iterations.
Completed Foundation | Homepage and launch surfaces compacted with denser proof-led messaging inspired by modern security-training product patterns. | Completed | Completed | Delivered | Creates a stronger first impression, though brand and messaging can continue to mature.
In Progress / Current Sprint | Finalize the client-facing roadmap package and align the product narrative around what is demo-ready versus what remains to reach production depth. | In Progress | High | 4-6 hrs | This spreadsheet is part of that packaging work and should become the editable client planning artifact.
In Progress / Current Sprint | Continue refinements to the new Content Missions library experience so launch behavior, readability, and hierarchy remain stable as more curriculum is added. | In Progress | High | 8-16 hrs | The main redesign is complete, but the surface will need another pass when more real content is migrated.
In Progress / Current Sprint | Continue polish on the page-based training flow so lesson transitions, progress states, and in-course content density feel more intentional across all modules. | In Progress | High | 12-24 hrs | This is especially important once the full seven-module curriculum is loaded in production depth.
In Progress / Current Sprint | Monitor the reusable coaching-log popup pattern across coach and manager flows and apply any follow-up adjustments found during stakeholder review. | In Progress | Medium | 6-10 hrs | The core workflow works, but client review may surface spacing or form-usability adjustments.
Queued / Roadmap | Migrate the full training curriculum into the LMS at production depth across all seven planned modules, including learner and leadership tracks. | Queued | High | 120-180 hrs | This is the single largest remaining body of work and likely the most important dependency for a production-ready rollout.
Queued / Roadmap | Create a structured content-ingestion and maintenance workflow so curriculum updates can be managed without repeated manual UI assembly. | Queued | High | 24-40 hrs | Recommended before or during full curriculum migration to prevent future bottlenecks.
Queued / Roadmap | Run a product-wide UI consistency pass across every role workspace, modal, card system, typography scale, spacing pattern, and state transition. | Queued | High | 40-60 hrs | The product is significantly improved, but it still needs a broader unification pass to feel fully coherent end to end.
Queued / Roadmap | Complete mobile and tablet responsiveness for priority workflows so the LMS is credible across common device sizes. | Queued | High | 32-48 hrs | Current work has been optimized primarily for desktop demo quality rather than full responsive production readiness.
Queued / Roadmap | Replace demo-style assumptions with production-grade authentication, SSO, tenant administration, and enterprise access-management controls. | Queued | High | 32-56 hrs | Critical for real enterprise deployment and stakeholder trust.
Queued / Roadmap | Connect reporting experiences to live operational data pipelines and define trustworthy source-of-truth metrics for coaching, QA, and learning outcomes. | Queued | High | 40-80 hrs | Current analytics storytelling is strong for demonstration, but production reporting needs validated live data integration.
Queued / Roadmap | Build exportable reporting outputs for client stakeholders, including spreadsheet, PDF, presentation, or email-ready summaries where appropriate. | Queued | Medium | 16-28 hrs | Important for operational adoption and client communications.
Queued / Roadmap | Implement a notification and reminder system for coaching actions, assignment nudges, escalations, and manager follow-through. | Queued | Medium | 24-40 hrs | Would materially improve day-to-day usefulness beyond demo interactions.
Queued / Roadmap | Create admin-facing content and program management tools so non-developers can manage modules, briefs, assignments, and supporting artifacts. | Queued | High | 36-60 hrs | This reduces long-term dependence on engineering for routine curriculum changes.
Queued / Roadmap | Deepen coaching workflow functionality with edit history, approvals, linked action plans, attachment support, and richer cadence management. | Queued | Medium | 24-36 hrs | The current workflow proves the interaction model, but operational maturity will need more depth.
Queued / Roadmap | Expand learner training states with stronger progress persistence, assignment orchestration, recommendation logic, and completion governance. | Queued | Medium | 24-40 hrs | Important once the full curriculum and real user traffic are in place.
Queued / Roadmap | Run a formal accessibility review covering color contrast, keyboard navigation, focus management, semantic structure, and assistive-technology behavior. | Queued | High | 20-32 hrs | Recommended before external rollout so remediation is built into the next polish cycle.
Queued / Roadmap | Perform performance optimization for large single-page views, training media loads, and state-heavy dashboards as real content volume increases. | Queued | Medium | 18-30 hrs | Especially relevant because the main UI currently lives in a very large view file.
Queued / Roadmap | Refactor oversized UI and router files into more maintainable feature modules to improve delivery speed and reduce regression risk. | Queued | Medium | 28-44 hrs | This is a technical-health investment that will make future roadmap delivery safer.
Queued / Roadmap | Add stronger QA coverage for role-specific end-to-end scenarios, reporting accuracy checks, and curriculum-content regression verification. | Queued | High | 24-40 hrs | Useful before introducing a larger body of curriculum and more production-oriented integrations.
Queued / Roadmap | Prepare production hardening work across environment configuration, error monitoring, data backup practices, auditability, and release readiness. | Queued | High | 30-50 hrs | Necessary for moving from persuasive demo environment to a dependable production program.

## Roadmap Totals
Roadmap Effort Snapshot
Category | Approx. Open Items | Combined Estimate | Commentary
Current sprint follow-up | 4 | 30-56 hrs | Covers packaging, Content Missions stabilization, training-flow polish, and popup workflow follow-up.
Curriculum and content migration | 2 | 144-220 hrs | Includes full seven-module curriculum migration plus a sustainable content-ingestion workflow.
Experience polish and responsiveness | 2 | 72-108 hrs | Includes product-wide UI consistency work and mobile/tablet responsiveness.
Enterprise functionality and operations | 7 | 186-330 hrs | Includes SSO/auth depth, live data integration, exports, notifications, admin tools, learner/workflow depth, and production hardening.
Quality, accessibility, and maintainability | 4 | 90-146 hrs | Includes accessibility review, performance optimization, refactoring, and expanded QA coverage.
Overall planning range | 19 open roadmap items | 522-860 hrs | Directional estimate only. The total will move based on curriculum-source readiness, stakeholder reviews, and production integration scope.